## Gantt Chart
Gantt Chart - Integrated OS Learning Management System
Legend: | Start | In Progress | End
Task ID | Task Name | Start Date | End Date | MARCH 2026 |  |  |  | APRIL 2026
|  |  |  | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5
T01 | SYSTEM PLANNING & DESIGN
T01.1 | Plan System Design & Goals | 3/25/26 | 3/26/26 | bar: MARCH 2026 W4
T01.2 | Identify Modules (CPU, Memory, Deadlock) | 3/25/26 | 3/26/26 | bar: MARCH 2026 W4
T01.3 | Create System Workflow | 3/25/26 | 3/26/26 | bar: MARCH 2026 W4
T01.4 | Design UI Layout (Wireframe) | 3/25/26 | 3/26/26 | bar: MARCH 2026 W4
T01.5 | Design Database | 3/25/26 | 3/26/26 | bar: MARCH 2026 W4
T02 | DATABASE DEVELOPMENT
T02.1 | Create Users Table | 3/27/26 | 3/28/26 | bar: MARCH 2026 W4
T02.2 | Create Simulations Table | 3/27/26 | 3/28/26 | bar: MARCH 2026 W4
T02.3 | Create Results Table | 3/27/26 | 3/28/26 | bar: MARCH 2026 W4
T02.4 | Setup Database Connection | 3/27/26 | 3/28/26 | bar: MARCH 2026 W4
T03 | USER AUTHENTICATION
T03.1 | Create Register Page | 3/28/26 | 3/29/26 | bar: MARCH 2026 W4 to MARCH 2026 W5
T03.2 | Create Login Page | 3/28/26 | 3/29/26 | bar: MARCH 2026 W4 to MARCH 2026 W5
T03.3 | Backend Authentication Logic | 3/28/26 | 3/29/26 | bar: MARCH 2026 W4 to MARCH 2026 W5
T03.4 | Session Handling | 3/28/26 | 3/29/26 | bar: MARCH 2026 W4 to MARCH 2026 W5
T04 | MODULE DEVELOPMENT
T04.1 | CPU Scheduling Module | 3/28/26 | 3/30/26 | bar: MARCH 2026 W4 to MARCH 2026 W5
T04.2 | Memory Management Module | 3/28/26 | 3/30/26 | bar: MARCH 2026 W4 to MARCH 2026 W5
T04.3 | Deadlock Simulation Module | 3/28/26 | 3/30/26 | bar: MARCH 2026 W4 to MARCH 2026 W5
T05 | SIMULATION FEATURES
T05.1 | Input Forms (All Modules) | 3/28/26 | 3/30/26 | bar: MARCH 2026 W4 to MARCH 2026 W5
T05.2 | Algorithm Processing Logic | 3/28/26 | 3/30/26 | bar: MARCH 2026 W4 to MARCH 2026 W5
T05.3 | Output Visualization | 3/28/26 | 3/30/26 | bar: MARCH 2026 W4 to MARCH 2026 W5
T06 | UI/UX DESIGN (HTML/CSS)
T06.1 | Dashboard Design | 3/28/26 | 4/6/26 | bar: MARCH 2026 W4 to APRIL 2026 W1
T06.2 | Module Pages Styling | 3/28/26 | 4/6/26 | bar: MARCH 2026 W4 to APRIL 2026 W1
T06.3 | Responsive Design | 3/28/26 | 4/6/26 | bar: MARCH 2026 W4 to APRIL 2026 W1
T07 | TESTING & FINALIZATION
T07.1 | System Testing | 3/28/26 | 4/6/26 | bar: MARCH 2026 W4 to APRIL 2026 W1
T07.2 | Bug Fixing | 3/28/26 | 4/6/26 | bar: MARCH 2026 W4 to APRIL 2026 W1
T07.3 | Final Deployment | 3/28/26 | 4/6/26 | bar: MARCH 2026 W4 to APRIL 2026 W1
T08 | POLISH & UX REFINEMENTS
T08.1 | Help System (? Popups Across All Pages) | 4/7/26 | 4/26/26 | bar: APRIL 2026 W2 to APRIL 2026 W4
T08.2 | Theme & Styling Fixes (Dark Mode, Cache-Busting) | 4/7/26 | 4/26/26 | bar: APRIL 2026 W2 to APRIL 2026 W4
T08.3 | Stability Fixes (ViewState Handler, Null-Ref, Empty States) | 4/7/26 | 4/26/26 | bar: APRIL 2026 W2 to APRIL 2026 W4